## Sheet1
Task Name | Task Description | Date Created | Estimate (Days) | Team Member | Date Started | Date Finished | Comments/Notes
Project Pre-coding stage
Problem statement | Writting down the problem statement for our project | 2020-02-03 | 1 | Lesley Bererra | 2020-02-03 | 2020-02-04
Overall Web Page Design | Create the main layout of the website | 2020-02-03 | 1 | Guido Prado | 2020-02-03 | 2020-02-04
Home page characteristics | Description of the home page characteristics | 2020-02-03 | 1 | Bailin Wu | 2020-02-20 | 2020-02-21
Pressing of "Shop" button | Pre-Coding stage: Conceptualize the look and action of the "Shop" button | 2020-02-03 | 1 | Yuchao Yan | 2020-02-20 | 2020-02-21
Virtual shopping cart | Pre-Coding stage: Listing and describing the component of the virtual chopping cart | 2020-02-03 | 1 | Yuchao Yan | 2020-02-20 | 2020-02-21
Checkout page | Pre-Coding stage: Description of the checkout system/page | 2020-02-03 | 1 | Bailin Wu | 2020-02-20 | 2020-02-21
Usage details | Pre-Coding stage: Identify and list different usage scenareo when consumer use our website | 2020-02-03 | 1 | Makayla Walton | 2020-02-02 | 2020-02-03
Usage Flowchart | Pre-Coding stage: Creation of a usage flowchart showing what would happen when a user goes into the website | 2020-02-03 | 1 | Guido Prado | 2020-02-07 | 2020-02-08
Component architecture diagram | Pre-Coding stage:Breakdown of software component Information | 2020-02-03 | 1 | Jooyul Yoon | 2020-02-07 | 2020-02-08
Component Design and Description | Pre-Coding stage:Creation of pseudocode, basic logic of website flow | 2020-02-03 | 1 | Yuchao Yan | 2020-02-07 | 2020-02-08
Component Design and Description | Pre-Coding stage: Break down component design information from (High Level Design) | 2020-02-03 | 1 | Bailin Wu/Yuchao Yan | 2020-02-20 | 2020-02-21
Architecture / High-level Design | Pre-Coding stage: listing and give description of Hardware and software and famework being used | 2020-02-03 | 1 | Bailin Wu | 2020-02-07 | 2020-02-08
Coding Stage
High Level Design Test Plan | Listing the function of Online Food Store need to be tested | 2020-02-04 | 1 | Yuchao Yan | 2020-02-21 | 2020-02-22
Test plan scenarios | Listing scenario of the potential error customer will face | 2020-03-10 | 1 | Makayla Walton / Bailin wu | 2020-03-22 | 2020-03-23
Description of test strategy | Describing what our test strategy is based on | 2020-03-10 | 1 | Guido Prado | 2020-03-20 | 2020-03-21
Low Level Design Document | Pseudocode Logic | 2020-03-10 | 2 | Snoop Jooyul Yoon | 2020-03-22 | 2020-03-24
Register and Login Front end | initial demo for registration and login | 2020-03-10 | 2 | Guido Prado | 2020-04-10 | 2020-04-11
home page code | write out code for the home page that the user would initially see when using our website | 2020-04-23 | 2 | Makayla Walton | 2020-04-21 | 2020-04-23
home page layout | use the code to design the homepage layout (images/icons/buttons/tab loactions) | 2020-04-23 | 2 | Lesley Bercerra / Makayla Walton | 2020-04-21 | 2020-04-23
home page picture design | The main picture on our homepage screen | 2020-04-23 | 1 | Lesley Bercerra | 2020-04-23 | 2020-04-23
back end | product table: | 2020-04-10 | 5 | Yuchao Yan | 2020-04-14 | 2020-04-14
1.) structuring positioning of Prodocuts
2.) Implementing Adding Button and number entering button
3.) Place photo of product base on product possition
4.) Adding information of product to its posittion
back end | Creating database | 2020-03-20 | 3 | Jooyul Yoon | 2020-03-20 | 2020-03-23
back end | Backend Logic: Connecting sign up, login, logout function to Data base and storing the infomation | 2020-04-10 | 7 | Jooyul Yoon | 2020-04-10 | 2020-04-17
front end | Implementing Front end logic : Creating structure of Shopping Pag and Checkout Page | 2020-04-10 | 5 | Yuchao Yan | 2020-04-20 | 2020-04-26
1.) Responsive table with product name, amount, price and weight
2.) Placement of remove button and checkout button
back end | Implementing BackEnd Logic: Connect Shopping cart and shopping page | 2020-04-23 | 3 | Jooyul Yoon | 2020-04-23 | 2020-04-26
1.) Imcrementing of amount and weight of product base on user's choice in shopping page
2.)Connection to Check out page, prompting user to enter personal shipping information
back end | remove item from cart remove from db | 2020-04-26 | 3 | Jooyul Yoon | 2020-04-26 | 2020-04-29
back end | After chcekout reset db | 2020-04-29 | 3 | Jooyul Yoon | 2020-04-29 | 2020-05-02
Post_Coding Stage
Creating lay out of User Guide | List and placement of Category of User guide | 2020-04-29 | 7 | Lesley Bercerra | 2020-05-01 | 2020-05-08
Adding user guide of different part of user guide | description of registration on user guide | 2020-04-29 | 7 | Guido Prado | 2020-05-01 | 2020-05-08
| description of login on user guide | 2020-04-29 | 7 | Guido Prado | 2020-05-01 | 2020-05-08
| description of user Shopping Guide | 2020-04-29 | 7 | Bailin Wu / Makayla Walton | 2020-05-01 | 2020-05-08
| description of user Check out Guide | 2020-04-29 | 7 | Bailin Wu | 2020-05-01 | 2020-05-08
| Usage Scenario | 2020-04-29 | 7 | Everyone on Team | 2020-05-01 | 2020-05-08
| Frequently asked questions | 2020-04-29 | 7 | Everyone on Team | 2020-05-01 | 2020-05-08
| Adding Picture to the user guide | 2020-04-29 | 7 | Lesley Bercerra | 2020-05-01 | 2020-05-08
User Guide Video | Recording VIdeo | 2020-04-29 | 1 | Yuchao Yan | 2020-05-01 | 2020-05-08